## Port_Swap_Estimates
SI | Port Swap Component | Story Point Estimate | Business Day Estimate | Technology Day Estimate | Owner | Description | Assumption | Notes | Outstanding Items | Dependency (Can this be worked separately by business without impact)
1 | Port Swap Contract Analysis |  | 3 | 5 | Business/Technology | For this book of work we need to determine the process we will implement for creating the Port Swap contracts in Calypso for all Trading Books and dealers. Need to ensure the setup accounts for all variations of Port Swaps that the desk could trade ie Currencies, Liquidation method, Commission methods, Dividend payment method etc | New req port swap contract by [Dealer], [Portfolio], [Settle Ccy], and [Maturity Date]. Based on this requirement it appears the best path forward will be to automate this solution. |  | Where do we source Port Swap Contract data? | Yes
2 | Port Swap Contract Implementation |  | 6 | 30 | Business/Technology/Nasdaq | Need to implement process for creating universe of all Port Swap contracts in Calypso. Ensure that all Port Swap fields are populated as expected. | Assuming we have required data from CRD. | Hard to estimate business effort without it solutioned but putting estimated effort based off current understanding. Need to handle applicable FX Rate Resets. |  | Yes
3 | Port Swap Contract Testing |  | 3 | 5 | Business | Test flavor of each Port Swap contract in Calypso. Ensure each one is setup with the correct values to meet trading requirements. |  |  |  | Yes
4 | Port Swap Underlying Analysis |  | 2 | 0 | Business/Technology | Assess the underlying's in scope. Currently Equities and Equity Indices setup in Calypso but does this include the universe. Are depositary receipts or Future Equity Index's in scope as Calypso supports them? |  |  | Are depositary receipts or Future Equity Index's in scope as Calypso supports them? | Yes
5 | Port Swap Underlying Implementation |  | 3 | 0 | Business/Technology/Nasdaq | Need to implement process for creating universe of all Port Swap underlying's in Calypso. Based on current infrastructure this may not be needed? |  |  |  | Yes
6 | Port Swap Underlying Testing |  | 3 | 0 | Business | Validate each underlying flavor is created as expected, field and attributes populated as expected. |  |  |  | Yes
7 | Port Swap Trade Analysis |  | 3 | 5 | Business | Complete analysis on process for how to automate Port Swap trade capture. Need to investigate the OMS's in scope, flavors the desk will trade, func that will need to be created, process for replay func or error monitoring. |  | How many OMS's Flavors? Volume? | How many OMS's in scope? Example file per Port Swap trade flavor? | Yes
8 | Port Swap Trade Mapping and Implementation |  | 4 | 10 | Business/Technology | Complete Trade CDUF mapping against OMS's in scope and development team will code so that middleware can receive Trade file from OMS and trade will be converted into CDUF and loaded into Calypso. |  |  |  | Yes
9 | Port Swap Trade Testing |  | 5 | 5 | Business | Validate each trade flavor is created as expected, stp's to right Status, expected attributes and keywords are populated. |  |  |  | Yes
10 | Port Swap liquidation Analysis |  | 2 | NA | Business | Agree on Liquidation method that needs to be used for Port Swaps across dealers. | Assumption is implementing one liquidation method for all Port Swaps regardless of broker. |  | Liquidation method in scope. Do any current products in Calypso use this position based functionality? Are there any active positions that we have to worry about Migrating? | No
11 | Port Swap liquidation Analysis Implementation |  | 5 | NA | Business | Configure required liquidation config, position specification, engine attributes, trade filters required to aggregate and liquidate Port Swap contracts. Ensure solution does not affect any other positional based products in Calypso. | Positions will be aggregated at Port Swap Contract, book, broker and underlying equity level. |  |  | No
12 | Port Swap liquidation testing |  | 5 | NA | Business | Complete testing with a variety of positions to ensure that positions getting aggregating as expected. Validate liquidation engine is liquidating the relevant tax lots and generating the expected transfers. Regression test that any other positional based products are unaffected by changes. |  | Do we need any specific reporting to provide Realized Cash transfers based upon tax lot liquidation. |  | No
13 | Port Swap Pricing Analysis |  | 2 | 0 | Business | Analyze what Market Data is required for these trade types. At a minimum we will need Equity, Rate Index and FX rates. Market data for these instruments is currently available but need to assess if universe of instruments is covered or if there is new pricing requirements that would require new quotes and/or new Quote set as don't want to impact existing processes. |  | Equity prices might be done. Analyze FX rates and if new req or new quote set is needed. Might already be there. Already in there but might need new price on time req so need new quote set. | Current market data solution for FX rate, Rate Index and Equity prices sufficient? Are we affected with upcoming changes in market data source? | Yes
14 | Port Swap Pricing Implementation |  | 3 | 0 | Business/Technology | Depending on analysis above will need to determine if any changes are required to current process and if so we will need to account for the development/configuration work in this book of work. |  | Hard to estimate business effort without it solutioned but putting estimated effort based off current understanding. |  | Yes
15 | Port Swap Pricing Testing |  | 3 | 0 | Business | Validate all expected market data flowing into Calypso against an agreed benchmark to ensure value, quote set, quote type is populated as expected. |  | Include Cashflow validation, FX rate. |  | Yes
20 | Port Swap Valuation Analysis |  | 2 | NA | Business | Analyze what valuation measures are needed for downstream and EMIR reporting. |  | NPV, NPV funding leg and NPV performance leg. | What Valuations are required to be output. | Yes
21 | Port Swap Valuation Configuration |  | 3 | NA | Business | Configure Pricing environment, pricer configuration, parameters to price all expected trades |  |  |  | Yes
22 | Port Swap Valuation Testing, Validation and Sign-off |  | 5 | NA | Business/Pricing team | Compare each Port Swap trade valuations against baseline trades and get sign off from Pricing team on Calypso's calculations. |  | Book flavors of all trades, confirm valuations and match against pricing team expectations. |  | Yes
13 | Neoxam Valuation Reporting Analysis |  | 2 | 3 | Business | Neoxam will need to receive Gain/Loss valuations from Calypso. Portfolio Swap attributes may also be needed. |  |  | Will need to define what attributes are needed in the report and what valuations are needed. Is it just NPV loss/gain? | Yes
14 | Neoxam Valuation Reporting Implementation |  | 3 | 4 | Business/Technology | Configuration of report(s) that need to be sent to Neoxam. Deveolpemnt work needed for MW team to pick up reports from the Calypso cloud folder and send the reports to Neoxam |  |  | Will need to define what attributes are needed in the report and what valuations are needed. Is it just NPV loss/gain? Report requirement for timings also needed. | No
15 | Neoxam Valuation Reporting Testing |  | 20 | 3 | Business | Testing that the reports generated from Calypso have all the correct columns and that the valuations in the report are correct. Also need to test the flow of the reports from Calypso to Neoxam |  | Will need to work with MW team as part of testing. |  | No
13 | STT Trade Reporting Analysis |  | 2 | 5 | Business | Trade report containing specific trade info. New and Cancel trades required to be on the report |  |  | Will need to define what trade attributes are needed in the report? | Yes
14 | STT Trade Reporting Implementation |  | 3 | 10 | Business/Technology | Configuration of trade report(s) that need to be sent to SSB. Deveolpemnt work needed for MW team to pick up reports from the Calypso cloud folder and send the reports to SSB |  |  | Will need to define what trade attributes are needed in the report? Report requirement for timings also needed. | Yes
15 | STT Trade Reporting Testing |  | 20 | 5 | Business | Testing that the reports generated from Calypso have all the correct columns and that both Cancel and New trades are included. Also need to test the flow of the reports from Calypso to SSB |  | Will need to work with MW team as part of testing. |  | Yes
13 | STT Reset Reporting Analysis |  | 2 | 3 | Business | Transfer report containing specific Cashflow info. |  |  | Will need to define what transfer info/attributes are needed in the report? | Yes
14 | STT Reset Reporting Implementation |  | 3 | 4 | Business/Technology | Configuration of transfer report(s) that need to be sent to SSB. Deveolpemnt work needed for MW team to pick up reports from the Calypso cloud folder and send the reports to SSB |  |  | Will need to define what transfer info/attributes are needed in the report? Report requirement for timings also needed. | Yes
15 | STT Reset Reporting Testing |  | 10 | 3 | Business | Testing that the reports generated from Calypso have all the correct columns. Also need to test the flow of the reports from Calypso to SSB |  | Will need to work with MW team as part of testing. |  | Yes
16 | Port Swap Workflow |  | 3 | NA | Business | Configure Port Swap Trade, Transfer and Message Workflow to account for all Trades from the desk and also lifecycle events. |  | No Swift messaging is required. |  | No
17 | Port Swap lifecycle Analysis |  | 2 | 15 | Business/Technology | Identify all the applicable lifecycle actions for Port Swaps and the underlying equities. |  |  |  | Yes
18 | Port Swap lifecycle Implementation |  | 1 | 10 | Business/Technology | Ensure middleware system can process all OMS lifecycle events and apply subsequent event in Calypso. |  | New, Cancel |  | Yes
19 | Port Swap lifecycle Testing |  | 3 | 5 | Business/Technology | Test flavor of each lifecycle event and validate results in Calypso. |  | Rate resets here. Need more info reqs here Termination, Rollover, Dividends, stock split etc |  | Yes
23 | Configure Dummy SDI's forPort Swap |  | 1 | NA | Business | Build Dummy SDI structure to enable all Port Swaps to flow to Verf status for all Fund and Brokers in scope. |  |  |  | No
24 | Task station |  | 1 | NA | Business | Configure task station tabs for any operation requirements such as Trade entry failures, Trades/Transfers stuck in Non Verf status. |  |  |  | No
25 | Reporting |  | 2 | NA | Business | Configure reporting func for operations and downstream users. Needs requirements but could include Trade, Transfer, Cashflow and Positional based reports. |  |  |  | No
26 | Calypso connectivity component |  | 0 | 0 | Reliant on Nasdaq | Placeholder card to estimate any work that requires Nasdaq involvement such as environment issues, connectivity with market data servers, routing for OMS trades etc |  |  | Placeholder Item for Calypso involvement on this initiative. Team needs to estimate buffer for this | Yes
27 | Create any missing static |  | 2 | NA | Business | Placeholder card in case any missing static is required such as Fund, Broker, Account, Contact setup. |  |  |  | No
29 | Estimate for VM+IM+IA margining for Port Swaps |  | 40 | 10 | Business/Nasdaq | Need to understand from Calypso if it supports VM+IM+IA margining for Port Swaps in Collateral Manager. Based on this need to estimate scope of this work. |  |  | Nasdaq to opine if they support Port swaps from collateral perspective on v17 and if not provide solution and time it will be available for team to estimate work effort. | Yes
30 | SEC SBS estimate for collateralization |  | 20 | NA | Business/Nasdaq | Need to understand from Calypso if it supports SEC SBS Margin for Port Swaps. Based on this need to estimate scope of this work. |  |  | Nasdaq to opine if they support Port swaps from collateral perspective on v17 and if not provide solution and time it will be available for team to estimate work effort. | Yes
31 | Veris update to support Port Swaps trading |  | 40 | NA | Nasdaq | Mentioned in conversations. Not sure scope of this and how to estimate. |  | Work with Steve on estimating this. | Nasdaq to opine if they support Port swaps from collateral perspective on v17 and if not provide solution and time it will be available for team to estimate work effort. | Yes
32 | Tax withholding requirements |  | 5 | NA | Business | Flesh out Tax withholding requirements for books located in different locations eg Europe Versus US. How is tax withholdings currently applied in system for other applicable products? |  | Hard to estimate business effort without it solutioned but putting estimated effort based off current understanding. | Need to flesh out Tax withholding requirements and how we want it to be applied in Calypso. Need to outreach to dealers. | No
33 | FX reset |  | 3 | NA | Business | Ensure Calypso has required FX resets and FX fixing configuration to handle expected FX functionality. Automate Rate Reset and Price Fixing/. |  | Need to ensure FX Reset logic is handled in Port Contract Mapping. |  | No
34 | Cashflows Reset Dates for Early terminations. |  | 3 | NA | Business | Explore functionality on deferring cash flows on Port Swaps to the reset dates in the event of early terminations. |  |  |  | No
35 | Analyze required cashflows |  | 3 | NA | Business | RELALIZED GAIN or LOSS, BASIC INTEREST, FUNDING CHARGE, BORROW CHARGE, PERFORMANCE FLOWS, DIVIDEND FLOWS |  | Hard to estimate business effort without it solutioned but putting estimated effort based off current understanding. |  | No
36 | Netting requirements |  | 2 | NA | Business | Analyze any requirements surrounding netting of transfers. |  | Hard to estimate business effort without it solutioned but putting estimated effort based off current understanding. | Are there any netting specific requirements associated with Port Swaps? | No
37 | Corporate Action Analysis |  | 3 | NA | Business | Analyze the Corporate action requirements and validate Calypso's ability to generate the following CA's: • Cash Dividend (DVCA) • Stock Split (SPLF) • Reverse Stock Split (SPLR) • Spin-Off (SOFF) • PERFORMANCE (PRICE-CHANGE) | The list of CAs supported for PFS are: • Cash Dividend (DVCA) • Stock Split (SPLF) • Reverse Stock Split (SPLR) • Spin-Off (SOFF) • PERFORMANCE (PRICE-CHANGE) | Hard to estimate business effort without it solutioned but putting estimated effort based off current understanding. | Currently only Dividend CA's for ELS are able to be processed in Calypso, we need to verify if there is an issue for other CA types in Calypso. We need to verify with the business if these CA's are needed for day 1. | No
38 | Is there any Risk component in Calypso that Port Swaps need to be added to? |  | 4 | NA | Business | Validate current risk setup for products trades and ascertain if Futures needs to be added based off requirements. |  | Hard to estimate business effort without it solutioned but putting estimated effort based off current understanding. | Unsure on current Risk func used in Calypso. Need to understand if product needs to be added to any? | No
39 | Corporate Action - Cash Dividend (DVCA) |  | 2 | NA | Business | Build and test config or process to handle Cash dividend events on underlying instruments for Port Swap Contract | The list of CAs supported for PFS are: • Cash Dividend (DVCA) • Stock Split (SPLF) • Reverse Stock Split (SPLR) • Spin-Off (SOFF) • PERFORMANCE (PRICE-CHANGE) | Hard to estimate business effort without it solutioned but putting estimated effort based off current understanding. | Need to understand current process? What is the ideal Future state for Cash Dividends and can Calypso solution be built for this. | No
40 | Corporate Action - Stock Split (SPLF) |  | 2 | NA | Business | Build and test config or process to handle Cash dividend events on underlying instruments for Port Swap Contract | The list of CAs supported for PFS are: • Cash Dividend (DVCA) • Stock Split (SPLF) • Reverse Stock Split (SPLR) • Spin-Off (SOFF) • PERFORMANCE (PRICE-CHANGE) | Hard to estimate business effort without it solutioned but putting estimated effort based off current understanding. | Need to understand current process? What is the ideal Future state for Cash Dividends and can Calypso solution be built for this. | No
41 | Corporate Action - Reverse Stock Split (SPLR) |  | 2 | NA | Business | Build and test config or process to handle Cash dividend events on underlying instruments for Port Swap Contract | The list of CAs supported for PFS are: • Cash Dividend (DVCA) • Stock Split (SPLF) • Reverse Stock Split (SPLR) • Spin-Off (SOFF) • PERFORMANCE (PRICE-CHANGE) | Hard to estimate business effort without it solutioned but putting estimated effort based off current understanding. | Need to understand current process? What is the ideal Future state for Cash Dividends and can Calypso solution be built for this. | No
42 | Corporate Action - Spin-Off (SOFF) |  | 2 | NA | Business | Build and test config or process to handle Cash dividend events on underlying instruments for Port Swap Contract | The list of CAs supported for PFS are: • Cash Dividend (DVCA) • Stock Split (SPLF) • Reverse Stock Split (SPLR) • Spin-Off (SOFF) • PERFORMANCE (PRICE-CHANGE) | Hard to estimate business effort without it solutioned but putting estimated effort based off current understanding. | Need to understand current process? What is the ideal Future state for Cash Dividends and can Calypso solution be built for this. | No
43 | Corporate Action - PERFORMANCE (PRICE-CHANGE) |  | 2 | NA | Business | Build and test config or process to handle Cash dividend events on underlying instruments for Port Swap Contract | The list of CAs supported for PFS are: • Cash Dividend (DVCA) • Stock Split (SPLF) • Reverse Stock Split (SPLR) • Spin-Off (SOFF) • PERFORMANCE (PRICE-CHANGE) | Hard to estimate business effort without it solutioned but putting estimated effort based off current understanding. | Need to understand current process? What is the ideal Future state for Cash Dividends and can Calypso solution be built for this. | No
44 | Tri-Resolve |  | 3 | NA | Business | Enable Tri-Resolve reporting for Port Swap product line. Need to build out existing functionality to handle new product type. Solution needs to be tested and validated to ensure it meets requirements from business. |  |  |  | No
46 | Estimating Migrating Open ELS to Port Model Analysis |  | 3 | NA | Business | Desk currently has an estimated 140 ELS trades open currently. Analysis required on if we need to migrate these trades over to Port Swaps model. Need to analyze impact, workload required in this, downstream impact, Does PM need to update structure on their OMS? |  | Includes testing for downstream impacts. | Any impact on liquidation on migrating over just open ELS? | No
47 | Migrating Open ELS to Port Model Implementation |  | 7 | 3 | Business | Close out Existing ELS Positions. Create the new positions as Port Swaps and ensure that trades are mapped correctly and aggregation is correct. | We will migrate over existing ELS products to Port Swap model in Calypso. Have to handle downstream distribution and allign with other platforms that receive transaction entries from Calypso. |  | Need to understand liquidation order for migration so future events liquidate in correct order? Any audit or downstream events we need to suppress or distribute? If PM doesn't change trade issue in getting lifecycle on ELS? | No
48 | Migrating Open ELS to Port Model Testing |  | 7 | 3 | Business | Validate migration effort in lower env to ensure results are as expected and no operational impact has occurred. |  |  |  | No